## Sheet1
Task Manager / Dev | Task Description | Initial Estimate(Hr) | Amount Remaining After…
|  |  | Day 4 | Day 8 | Day 12 | Day 16 | Day 20 | Day 24 | Day 28
Colby | Improve contrast on UI between text and background/resize UI | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Colby | Modify size and font for text | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sam | Merging sign in and sign up into same page | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sam | Alter landing page to have just one sign in button | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Aayush | Move buy button to a separate page | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Aayush | Implement server | 1.5 | 1 | 1 | 1 | 1 | 0 | 0 | 0
Aayush | Implement client | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
Aayush | Established basic interaction between client-server | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
Aayush | Implemented mock server for testing | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 0
Colby | Design ZMQ crypto data | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
Colby | Design ZMQ login | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0
Sam | Design ZMQ signup | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0
Sam | Design ZMQ logout | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
Sam | Design ZMQ buy | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Liam | Design ZMQ sell | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Colby | Design ZMQ add funds | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1 | 1 | 0
Colby | Design ZMQ view portfolio | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2 | 1.5 | 0
Liam | Disable login and logout buttons appropriately | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Colby | Allow for the storing of account information on server | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0
| Estimate Totals | 28.5 | 24 | 22 | 20 | 18 | 11 | 7.5 | 4 | 0 | 0 | 0 | 0 | 0
Task Manager / Dev | Task Description | Actual Time(Hr) | Amount Remaining After… Day 4: Date of Work
Colby | Changed the contrast between text and background | 0.5 | Amount Remaining After… Day 4: 2025-03-12
Colby | Modifed font and text size for UI | 0.5 | Amount Remaining After… Day 4: 2025-03-12
Sam | Merging sign in and sign up into same page | 0.5 | Amount Remaining After… Day 4: 2025-03-12
Sam | Alter landing page to have just one sign in button | 0.5 | Amount Remaining After… Day 4: 2025-03-12
Sam | Design ZMQ login | 4 | Amount Remaining After… Day 4: 2025-03-28
Sam | Design ZMQ signup | 4 | Amount Remaining After… Day 4: 2025-03-28
Aayush | Move buy button to a separate page | 2 | Amount Remaining After… Day 4: 2025-03-12
Aayush | Implement Server | 0.5 | Amount Remaining After… Day 4: 2025-03-27
Aayush | Implemented Client | 1 | Amount Remaining After… Day 4: 2025-03-27
Aayush | Established basic interaction between client-server | 0.5 | Amount Remaining After… Day 4: 2025-03-27
Aayush | Implemented mock server for testing | 4 | Amount Remaining After… Day 4: 2025-04-02
Colby | Design ZMQ crypto data | 0.5 | Amount Remaining After… Day 4: 2025-03-28
Colby | Design ZMQ login | 2 | Amount Remaining After… Day 4: 2025-03-24
Colby | Design ZMQ add funds | 2 | Amount Remaining After… Day 4: 2025-04-06
Colby | Design ZMQ view portfolio | 3 | Amount Remaining After… Day 4: 2025-04-08
Colby | Allow for the storing of account information on server | 2 | Amount Remaining After… Day 4: 2025-04-02
Liam | Disable login and logout buttons appropriately | 2 | Amount Remaining After… Day 4: 2025-03-12
Sam | Design ZMQ logout | 2 | Amount Remaining After… Day 4: 2025-04-08
| Actual Time Totals | 31.5