## Sheet1
Task Manager / Dev | Task Description | Initial Estimate(Hr) | Amount Remaining After…
|  |  | Day 4 | Day 8 | Day 12 | Day 16 | Day 20 | Day 24 | Day 28
Aayush | Implement Crypto Data Class | 1.5 | Amount Remaining After… Day 4: 0
Aayush | Implement Crypto manager class (Cryptos) | 1.5 | Amount Remaining After… Day 4: 0
Aayush | Allow for the storing of crypto data(File IO, later will be stored in server) | 1 | Amount Remaining After… Day 4: 1; Amount Remaining After… Day 8: 1; Amount Remaining After… Day 12: 1; Amount Remaining After… Day 16: 0
Aayush | Allow for the reading of crypto data (CSV file reader for now, later read in from server) | 1 | Amount Remaining After… Day 4: 1; Amount Remaining After… Day 8: 1; Amount Remaining After… Day 12: 1; Amount Remaining After… Day 16: 0
Sam | Allow for the storing of login information (username and pw) | 1.5 | 1.5 | 1.5 | 1 | 1 | 1 | 0 | 0
Sam | Allow for the verification of login information | 1.5 | 1.5 | 1.5 | 1 | 1 | 1 | 0 | 0
Colby | Design the user landing page | 1 | bar: Amount Remaining After… Day 4 to Amount Remaining After… Day 28
Sam | Design the log in page | 1 | bar: Amount Remaining After… Day 4 to Amount Remaining After… Day 28
Colby | Design the sign up page | 1 | bar: Amount Remaining After… Day 4 to Amount Remaining After… Day 28
Sam | Integrate the login process with the view | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0
Colby | Integrate the viewing of crypto data with the view | 3 | Amount Remaining After… Day 4: 3
Colby | Create the repository and setup a base java fx project | 1 | Amount Remaining After… Day 4: 0
Sam | Implement the Account class | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0
| Design the buy crypto page | 1.5 | Amount Remaining After… Day 4: 1.5
| Allow for the purchase of crypto(server will handle this later) | 1.5 | Amount Remaining After… Day 4: 1.5
Colby | Design the sell crypto page | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 | 0 | 0
Colby | Allow for the selling of crypto (server will handle this later) | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0
Colby | Design the portfolio page(page where investor can see their holdings) | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
| Estimate Totals | 27.5 | 23.5 | 14 | 13 | 6 | 4.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0
Task Manager / Dev | Task Description | Actual Time(Hr) | Amount Remaining After… Day 4: Date of Work
Colby | Create the repository and setup a base java fx project | 1 | Amount Remaining After… Day 4: 2025-02-12
Colby | Designed the landing page for the user | 1 | Amount Remaining After… Day 4: 2025-02-16
Colby | Designed the sign up page | 1.5 | Amount Remaining After… Day 4: 2025-02-17
Sam | Implemented Account class | 1 | Amount Remaining After… Day 4: 2025-02-15
Aayush | Implemented Crypto class | 1 | Amount Remaining After… Day 4: 2025-02-14
Aayush | Implemented Crypto manager class | 1 | Amount Remaining After… Day 4: 2025-02-14
Colby | Integrate the viewing of the crypto data to the view | 2 | Amount Remaining After… Day 4: 2025-02-26
Sam | Integrated the login process with the view | 3 | Amount Remaining After… Day 4: 2025-02-27
Aayush | Allow for storing of the crypto data | 1 | Amount Remaining After… Day 4: 2025-02-23
Aayush | Allow for reading the crypto data from a text file | 2 | Amount Remaining After… Day 4: 2025-02-23
Colby | Designed the portfolio page | 2 | Amount Remaining After… Day 4: 2025-02-28
Colby | Designed the sell page | 1 | Amount Remaining After… Day 4: 2/29/2025
Colby | Allow for the selling of crypto | 3 | Amount Remaining After… Day 4: 2025-03-05
| Actual Time Totals | 20.5