## Sheet1
Task Manager / Dev | Task Description | Initial Estimate(Hr) | Amount Remaining After…
|  |  | Day 4 | Day 8 | Day 12 | Day 14
Colby | Refactor the UI to display multiple crytocurrencies | 1 | 1 | 1 | 0 | 0
Colby | Implement cache to store crypto data | 2 | 2 | 2 | 0 | 0
Colby, Aayush | Refactor system to support adding cryptocurrencies dynamically | 2 | 2 | 1 | 0 | 0
Aayush | Add dynamic price change to cryptocurrencies. | 3 | 3 | 3 | 2 | 0
| Estimate Totals | 8 | 8 | 7 | 2 | 0
Task Manager / Dev | Task Description | Actual Time(Hr) | Date of Work
Colby | Refactor the UI to display multiple crytocurrencies | 1 | 2025-04-22
Colby | Implement cahce to store crypto data | 2 | 2025-04-20
Colby, Aayush | Refactor system to support adding cryptocurrencies dynamically | 2 | 2025-04-19
Aayush | Add dynamic price change to cryptocurrencies | 4 | 2025-04-23
| Actual Time Totals | 9